## Sheet1
Task | Lead | Due Date | Notes
Website Update Tastks
Update WC Stock status | PK | 2014-09-01
Update WC C: TAC | PK | 2014-09-01
Update WC Discards and Bycatch | PK | 2014-09-01
Update WC Observer Coverage | PK | 2014-09-01
Update NE Stock status 2013 | PK | 2014-09-01 | GB Cod, Summer Slounder, Summber flounder GB, Haddock, GB,
Update NE C:TAC 2013 | PK | 2014-09-01
Update NE Discards and bycatch 2013 |  | 2015-05-01 | National Observer Report Released March
Update NE Observer Coverage 2013 |  | 2015-05-01 | National Observer Report Released March
Update WC Stock Status 2014 | PK | 2015-03-01
Update WC C:TAC 2014 | PK | 2015-03-01
Upwdate NE Stock Status 2014 | PK | 2015-09-01
Update NE C:TAC 2014 | PK | 2015-09-01
Update NE Discards and bycatch 2014 |  | 2016-05-01 | National Observer Report Released March
Update NE Observer Coverage 2014 |  | 2016-05-01 | National Observer Report Released March
Research Tasks
Detailed WC Habitats and Effort Plan Plan | PK and TB | 2014-09-01
Detailed NE Habitats and Effort Plan | TE and PK | 2014-09-01
Work on WC habitats and effort | PK and TB |  | Last data year = 2013
Work on NE habitats and effort | TE and PK |  | Last data year = 2013
Publication Tasks
Characterizing effort changes in WC groundfish fishery | Peter K
Characterizing effort changes in NE groundfish fishery
Synthesis: comparative analysis of ecological indicators in two US catch share programs